Developed by: AJ Seaholm for KCRC 424 Races

Revised:  1-10-2010

- Long Lead Items

  - Sanction

  - Special Use Permit

  - Distribute flyers

  - RCU/NMPRA forum post about race

  - Budget approved by club members

  - Establish schedule on flyer

  - Pre-registration

  - Fuel purchase

  - APC Props for 424 event

  - Plywood for take-off pads

  - Caution tape/cones for off limit areas

  - Stakes/Posts for off limit areas

  - Trophies/Certificates with pictures of pilot and plane

  - PA announcer

  - Paul Herman Race Software V1.1.4 http://www.nmpra.org/Software/index.html

  - Starter and assistant

  - Lunch food arrangements

  - Advertising for spectators

    - Comcast and Time Warner

    - Channel 4/5

  - WORKER sign-ups

  - PARTICIPANTS invitations

- Race Day Items

  - Race Equipment

    - Radios X6 (charge batteries)

    - Lap Counter Flip boards X4

    - Stop watches

    - #1 light set up

    - Battery for #1 lights

    - Starter’s cage

    - Starter’s flag

    - 60 second clock

    - Lane stickers for lane identification

    - Heat number flip cards

  - PA system

  - Laptop

  - Printer/paper for heat cards

  - Printer/paper for Pilot Photos on trophies

  - Scale to weight aircraft

  - Fuel Station Tables

  - Tables for pilot registration, tech, and data entry

  - Extra chairs for workers (ask workers to bring chair)

  - Generator/Inverter

  - 4 Pop-ups/tents for lap counters, data entry, #1, #2, #3

  - Worker calling list

  - Pilot Prizes

  - Worker Prizes

  - AMA Registration forms

  - Fuel (2+ cases)

  - Trophies/Certificates and frames for trophies

  - APC Props

NIGHT BEFORE ACTIVITIES

- Set up course

- Establish parking zones

- Mow pilots area and #1/#2 workers area

RACE DAY ACTIVITIES

- 7:10am – Gates open

- 7:20am – Set-up lights, clock, registration station, PA system

- 8:00am – Registration opens

- 8:00am - Practice begins for registered pilots, announce practice rules (Max 8 on line, 2 aircraft in the air, 10-12 laps max)

- 9:00am – Workers meeting and training during practice

- 9:00am – Registration closes

- 9:15am – Practice ends

- 9:20am – Pilot’s meeting

- 9:45am – Group Photo

- 9:55am – Practice Heat

- 10:00am – First heat on the clock

PILOT’S MEETING NOTES

- Thank-you for coming and supporting our club’s Pylon Race

- Thank workers

- Thanks sponsors

- Explain practice rules again

- Advertise Saturday night BBQ - open to everyone

- Explain stickers and lane assignments

- Explain race procedure

  - There will be a FULL 60 second clock

  - Starter will get a nod from the pilots and has the authority to delay the start if necessary but BE READY.  If you get a late start, get turned around

  - Lanes 1 & 3 take off first on the odd rounds – on pilot cards – Green means first push,

  - Lane 2 will take off first on the even rounds – on pilot cards – Green means first push.

  - Early launch is a cut.

  - Show lap counters and how they function, if cut you need to see 10 laps.  ALWAYS Fly an insurance lap.

  - 1 cut, you must 11 laps to finish the race.

  - 2 cuts get up and off the course, don't land until the heat has finished.

  - Mid-airs.  The starter has the authority, if he tells you to land, LAND.

  - Re-flys.  If you get off the ground, you will be included in the re-fly.

  - Callers stay with your pilots during landing, direct traffic.  WATCH THE FENCE.

  - Land quickly, MINIMIZE circling until other planes are cleared.

- Explain staging area, don’t cross lines.

- DO NOT APPROACH OR EVEN THINK ABOUT CONFRONTING OUR WORKERS.  THIS IS GROUNDS FOR IMMEDIATE DISQUALIFICATION.

- Fueling station location

- Frequency check

- It's up to the pilot to hear his heat called and be ready.

- We will stop for a 45 minute lunch break at approximately 12:30pm at the end of a round.  Pilots try to eat early so we can get the course workers fed and relaxed for a few minutes.

- We are scheduled to fly 6 rounds today.

- SAFETY, SAFETY, SAFETY. HAVE FUN